## Sheet1
Sumaiya Tarannum Noor - Frontend, UX/UI, Backend, Database Design (Lead) Md All Mamun Ridoy - Frontend, Backend, Database Design (As per before) Imran Nur - Backend, Database Design (As per before) Technology Frontend - React.js Backend - Django (First Choice), Flask (2nd Choice) Database - MySQL (First Choice), PostgreSQL (Best for Production) Maintenance - GitHub Testing and Online Version - CPanel
Modules | Task | Time Needed
General User / Job Seeker / Visitor Module | 1. Job Seeker/General User database Ready - User table design | 1 day
| 2. Registration Backend - Sign Up System | 1.5 day
| 3. User Authentication - Login System | 2 days
| 4. Job Search (Keyword base + Priority Base + Tag Base) | 0.5 day
| 5. User Job Preference and Job Type Setup (Interesting Jobs) | 0.5 day
| 6. User Job Experience and Skill Setup | 0.5 day
| 7. User General Settings Setup - Username, icon, Self Introduction, Notification Preference | 1.5 day
| 8. User Work related Setting Setup - User Preference for work facilities and environment setup | 1 day
| 9. User Available working hours per day and Desire to continue working setup | 0.5 day
| 10. Privacy and Security Settings - User Personal Information add, update, delete | 1 day
| 11. User Email, Password Update for Authentication | 0.5 day
| 12. User Identity Verification | 2 days
| 13. User to user block | 1 day
14. Qualified invoice issuer registration number (This is available in Japan only)
| 15. User Reward Accept System Setup (User Getting paid for the job. | 2 days
After te completion of the task the user will receive the payment from the Hirer)
| 16. User Membersip Cancelation | 0.5 day
| 17. User NID Verification | Unknown
| 18. User Bank Account Info Setup | 2 days
| 19. User Reward Withdrawal System implementation (Via Bank Account) | 2 days
| 20. User Reward Withdrawal System Setup - Withdrawal via Transfer Application | 1 day
| 21. User Client management setup - Showing the list of hirer they have previously worked and currently working for. | 1 day
| 22. User Client Partner Relationship Establisment - After working for a certain amount of time or | 1 day
finishing certain tasks for the client the job seeker can become a partnerof the hirer, if the hirer approves
| 23. Showing the list for the jobs that they are interested in | 0.5 day
| 24. User can follow their clients other works. | 0.5 day
| 25. Showig the users list for the job that they are currently applying | 1 day
| 26. Showing the users list for their jobs that are in progress. | 0.5 day
| 27. Showing the users list for the jobs that they have finished. | 0.5 day
| 28. Pagination setup for the lists related to the job | 0.5 day
| 29. Pagination setup for the list related to reward. | 0.5 day
| 30. Pagination setup for client management | 0.5 day
| 31. User Applying for jobs | 2 days
| 32. User getting accepted for the job | 1 day
| 33. User Guide Setup | 1 day
| 34. User task progress setup (Timeline/bar etc) | 1 day
| 35. Client Search (Keyword, tag, task based) | 0.5 day
| 36. Message (ADVANCED) | 2 days
| 37. Email Notification Setup (If accepted at the job) | 2 days (it can be extended)
| 38. Notification (Socket) | 2 days
| 39. Follow User/Company (Real-time update without socket) / Socket | 1 day
| 40. Like a job / Add to interest (Real-time Update without socket) / Socket | 1 day
| 41. Switch Profile (Profile Switching between job seeker and hirer profile) | 1 day
| 42. User Fraud job reportin to the admin | 0.5 day
| 43. Interview show on user end | 1 day
General Module - 44 days
Admin Module | 1. Admin Dashboard Design | 1 day
| 2. Admin Dashboard necessary page add and design | 2 days
| 3. User List show, update, delete for admin dashboard | 1 day
| 4. Admin Dasboard Posted Job monitoring based on keyword, skills, tags (List show) | 0.5 day
| 5. Admin dashboard posted job update, delete | 1 day
| 6. Admin dashboard Hirer List show | 0.5 day
| 7. Admin dashboard Hirer list update, delete | 0.5 day
| 8. Admin Dashboard Payment transaction monitoring setup (Transaction between hirer and job seeker) | 2 days
| 9. Admin Dasboard Fraud job list show | 0.5 day
| 10. Admin dashboard fraud job list update, delete | 0.5 day
| 11. Admin dashboard fraud user list show | 0.5 day
| 12. Admin dashboard fraud user list update, delete | 0.5 day
| 13. Admin dashboard new tag add, tag list show, tag list delete | 0.5 day
| 14. Admin Login/Logout | 1 day
| 15. Separate the user list into Job Search and Hirer (Filtering) | 0.5 day
| 16. User List Search (Keyword Search) | 0.5 day
| 17. Home Page Info Setup from Admin Dasboard | 2 days
| 18. Admin Notification Setup | 2 days
19. If needed any more setup it will be included
| 20. Footer info update from admin panel | 1 day
| 21. Contact us info update from admin panel | 1 day
| 22. Interview Add, show in Admin Panel | 1.5 day
| 23. Interview edit, delete | 1 day
Admin Module - 22 Days
Hirer Module | 1. Databse design for user to seperate between the job seeker and the hirer. | 2 days
| 2. Job Registration | 2 days
| 2. Find a Worker | 1 day
| 3. Payment Option Setup | 3 days
| 4. Payment History Setup | 3 days
| 5. Report to the admin for fraud user. | 1 day
| 6. Checking For Further Intrigation | 1.5 day
Hirer Module - 14 days
Total Time Calculation
General Module - 44 days
Admin Module - 22 days
Hirer Module - 14 days
Total Time Needed - 80 days